## Slide 1
Erasmus+ Capacity Building projects
in the field of Higher Education
Call 2017
FINANCIAL MANAGEMENT OF THE GRANT
  Grant Holders' Meeting
Brussels, 29-30 January 2018

## Slide 2: Regulatory Framework
EACEA Documents Application Your documents
National legislation
&
Institutional regulation
Any prior authorisation from EACEA

## Slide 3
  OUTLINE
  1) Financing principles
  2) Actual costs
  3) Unit costs
  4) Management of the Grant
  5) Financial reporting
  6) Final grant
  7) Checks & Audits
  NB: Please note that this document has no legal value

## Slide 4
 | EUR
I STAFF COSTS | 340.000
II TRAVEL COSTS | 150.000
III EQUIPMENT | 150.000
IV COSTS OF STAY | 160.000
V SUBCONTRACTING | 50.000
TOTAL GRANT (total I-V) | 850.000
  BUDGET MODEL
  (Annex III of Grant Agreement)

## Slide 5
  1) Financing principles
  Funding rule & Financing approach
  Budget headings and ceilings
  Budget transfers
  Eligible / Ineligible costs

## Slide 6: Funding rule & Financing approach
Co-funding principle
Grant ≠ Total costs of the project
Grant
(combination of two different financing approaches)
AC: Actual costs (Equipment and Subcontracting)
UC: Unit Costs (Staff, Travel and Costs of stay)

## Slide 7
Staff costs (UC) | Max 40% of grant (Art I.3 of GA)
Travel costs (UC) | no ceiling
Costs of stay (UC) | no ceiling
Equipment (AC) | Max 30% of grant (Art I.3 of GA)
Sub-contracting (AC) | Max 10% of grant (Art I.3 of GA)
  Budget headings and ceilings

## Slide 8: Budget Transfers (between budget headings)
Increase
UP to 10%
Even above the ceilings (for staff, equipment and subcontracting)
No prior authorization
  Amendment
    Ceilings cannot be exceeded
Increase by MORE than 10%
Staff costs | % of total grant in G.A. | Proposed increase | Effect on % of total grant | Decision
Max ceiling: 40% | 30% | +20% | 36% | Amendment possible
 | 35% | +20% | 42% | Not allowed

## Slide 9
Budget Transfers
Example 1 – amendment
 | EUR | % | Budget transfer | % of budget heading | result | % of total grant
I STAFF COSTS | 340.000 | 40% |  |  | 340.000 | 40%
II TRAVEL COSTS | 150.000 | 17,6% |  |  | 150.000 | 17,6%
III COSTS OF STAY | 150.000 | 17,6% | -10.000 |  | 140.000 | 16,5%
IV EQUIPMENT | 160.000 | 18,8% |  |  | 160.000 | 18,8%
V SUBCONTRACTING | 50.000 | 5,9% | +10.000 | +20% of budget heading | 60.000 | 7,1%
TOTAL GRANT (total I-V) | 850.000 |  |  |  | 850.000 | 

## Slide 10
Budget Transfers
Example 2 = NO need for amendment
 | EUR | % | Budget transfer | % of budget heading | result | % of total grant
I STAFF COSTS | 340.000 | 40% | +27.200 | +8% of 340.000 | 367.200 | 43,2%
II TRAVEL COSTS | 150.000 | 17,6% | -27.200 |  | 122.800 | 14,4%
III COSTS OF STAY | 150.000 | 17,6% |  |  | 150.000 | 17,6%
IV EQUIPMENT | 160.000 | 18,8% |  |  | 160.000 | 18,8%
V SUBCONTRACTING | 50.000 | 5,9% |  |  | 50.000 | 5,9%
TOTAL GRANT (total I-V) | 850.000 |  |  |  | 850.000 | 

## Slide 11
Eligible Costs
  Incurred during the eligibility period
  Foreseen in the application/budget
  In connection with the action/necessary for project implementation
  Identifiable, verifiable, recorded in accounting records
  Comply with requirements of tax and national legislation
  Reasonable, complying with sound financial management (economy and efficiency)
Article II.19.1 Grant Agreement

## Slide 12
1) Costs NOT fulfilling requirements of Art. II.19.1
2) Art. I.10.4/II.19.4
examples:
equipment such as: furniture, motor vehicles, alarm systems
costs linked to the purchase of real estate
activities not in project beneficiaries' countries (Annex IV), unless prior authorisation
Exchange losses
in kind contribution
excessive expenditure
deductible VAT
Ineligible Costs

## Slide 13
  QUIZ
  1) When declaring co-financing at final reporting stage, is there a minimum amount to declare?
  a. No
  b. Yes, an amount representing minimum 10% of the costs declared
  c. Yes, an amount representing minimum 10% of the costs declared, but only for unit costs
  2) Can I increase the staff costs for a project partner by 15% without requesting an amendment to the GA (if this is justified by the project activities) ?
  Yes, as far as the budget heading "staff costs" at project level does not increase by > 10% (and that the partnership agrees)
  No, never
  Yes, only if the staff costs of the partner do not exceed 40% of the total budget of the partner

## Slide 14
  2) Actual costs
  Definition
  VAT
  Exchange rate
  Tendering procedure
  Equipment
  Subcontracting

## Slide 15: Actual costs - Definition
Example:
Reported cost (laptops) of 1.500 EUR
=
Supporting documents to the value of 1.500 EUR
Expenses actually incurred
(Documented and justified with corresponding level of cost)

## Slide 16: VAT (Art. II.19.4 GA)
Check with NEO/EU Delegation if an agreement exists between the EU and the Partner Country
Ineligible
Unless
official document from competent authorities proving that the corresponding costs cannot be recovered

## Slide 17: Exchange rate (Art. I.10.2 GA)
2
Which exchange rate should be applied?
Rate to apply:
http://ec.europa.eu/budget/contracts_grants/info_contracts/inforeuro/index_en.cfm
EXAMPLE
1st Pre-financing: 23 Dec 2017 – 2nd Pre-financing: 22 Aug 2018
Invoice date: 09 January 2018 Applicable monthly rate: December 2017
All transactions must be declared in EUR in the Final Report
1) From start of eligibility period until receipt of second pre-financing:
monthly rate of reception of FIRST PRE-FINANCING
2) From date of receipt of second pre-financing until end of eligibility period: monthly rate of reception of SECOND PRE-FINANCING

## Slide 18: Procurement of goods/services
Less than 25.000 €
Best value for money
25.000 € - 134.000 €
Tendering procedure
More than 134.000 €
National Legislation

## Slide 19: Equipment
Total purchase cost (no depreciation)
Exclusively for Partner Country Higher Education Institutions
Recorded in inventory of institution
Labelled with E+ stickers
Installed (available for project participants) as soon as possible
Not foreseen in the application? Prior authorisation from Agency
Prior
Relevant to the objectives of the project foreseen in the application

## Slide 20: Subcontracting
Examples:
  Evaluation activities/auditing
  IT courses, Language courses
  Printing, publishing and dissemination activities
  Translation services
  Web design and maintenance
  Logistic support for the organisation of events
Not foreseen in the application? Prior authorisation from Agency
NO project-management related tasks
Implementation of specific tasks, by third party, to which a contract is awarded by one/several beneficiaries

## Slide 21: Supporting documents
Equipment
Invoice(s) and proof of payment
Subcontracting
Invoice(s) and proof of payment
Tangible outputs/products
> EUR 25.000 < EUR 134.000: tendering procedure and three quotations from different suppliers
EUR 134.000: procedure according to national legislation
Registration in the inventory
> EUR 25.000 < EUR 134.000: tendering procedure and three quotations from different suppliers
EUR 134.000: procedure according to national legislation
Travel activities of subcontracted service provider: copies of travel tickets, boarding passes, invoices and receipts
To keep with project accounts
To send with Final Financial statement:
EUR 25.000: copies of subcontract, invoice and competitive offers
Any prior authorisation from the Agency

## Slide 22
  1) Do I have to launch a tendering procedure for a contract value of 23,000 EUR?
  a. No, even if my institution requires to do it
  b. Yes, but the Agency should be informed
  c. No, unless my institution and/or the national legislation requires to do it
  2) Can a partner purchase equipment for another eligible partner?
  a. Yes, only if the project partner is a private HEI
  b. No, unless this was specified in the application
  c. Yes, if the cost effectiveness can be demonstrated and the equipment is delivered and recorded in the inventory of the partner country HEI.

## Slide 23
  3) Which supporting document do I need to keep to justify that an institution cannot recover VAT?
  a. A declaration signed by the legal representative of the institution
  b. An official document from the competent authorities
  c. A certificate from the financial department of the institution

## Slide 24
3) Unit costs
  Definition
  Staff costs
  Travel costs and costs of stay

## Slide 25: Unit cost - Definition
  No need to justify level of spending
  Financial control/audit declared unit costs supported with proofs of activities implemented
  Not divisible
  Fixed contribution multiplied by number of units,
  based on "Triggering events" (activities/outputs)

## Slide 26
Grant management cycle | UNIT COST | ACTUAL COSTS
Grant allocation | Based on estimated work programme | Based on the estimated budget
Grant Implementation | Beneficiary's own FINANCIAL "RECIPE" | Record costs actually incurred
Justification of the Grant | Based on activities actually implemented | Based on costs actually incurred
Partnership Agreement

## Slide 27
  If we have estimated 20 working days in the application for producing the qa strategy, which is the wrong statement?
  a. We will certainly be granted 20 days at the final report stage if we can produce the expected supporting documents and QA strategy
  b. We can declare a different nr. days in the final report
  c. The actual nr. of days granted will be decided on the basis of the actual outputs (QA strategy) and other supporting docs. and will never be more than the nr. of days declared

## Slide 28
  2) The actual costs for travel "x" are 30% higher than the value of the UC
  a. The EACEA should be informed so as to authorised a higher grant contribution
  b. You can increase the UC value by 30% and justify it in your final report
  c. You have to balance this loss with savings made under other activities funded by UC and/or with co-funding provided by the partnership

## Slide 29: Staff Costs
Unit cost = amount in Euro per working day per staff (not linked to the actual salary)
Calculation 3 variables: staff category, country, number of days
a) Categories: Managers, Researchers/Teachers/Trainers, Technical, Administrative nature of work performed, not status of individual
b) Country in which staff is employed, independently of where tasks are executed
c) Number of days proportioned to the work carried out
*Formal contractual relationship with a beneficiary organisation
  Contribution to Institutions for Staff* performing tasks necessary to achieve the objectives of the project

## Slide 30: Staff Costs
Example
A staff employed in Lithuania performing teaching activity for 3 days:
222 Euro (3 unit costs of 74 Euro each)
One working day according to national legislation (7 to 8 hours)
In principle max. 20 days/month or 240 days/year

## Slide 31: Staff costs - Exceptions
working conditions are similar to those of an employee
the result of the work belongs to the Institution
costs not significantly different from costs of regular staff
*Also applicable for students
Individuals* not regularly employed by partner institutions can be assigned to the project on the basis of a contract against payment if:

## Slide 32: Supporting documents
Staff Costs
Joint Declaration (EACEA template)
Time-sheets (EACEA template)
Proof of formal contractual relationship
Any evidence justifying the workload and activities/outputs (e.g. attendance lists for lectures given, tangible outputs / products, salary slips, etc.)
To keep with project accounts:
To send with Final Financial statement:
Any prior authorisation from the Agency

## Slide 33: Travel costs and Costs of Stay
  Calculation: 3 variables travel distance (travel costs), duration (costs of stay) and type of participant
Staff
  Under contract with beneficiary
  Travels intended for the activities listed in the Guidelines
  Duration: Max. 3 months
  Students
  Registered under beneficiary institutions
  Duration: Min. 2 weeks – Max. 3 months (Max. 1 week for short term activities linked to the management of the project)
  Eligible activities Guidelines section 3.3.1.2 (see tables)
Rules for Special Mobility Strand defined in separate Guidelines
Travel/stay for staff/students participating in eligible activities related to the achievement of the project

## Slide 34: Travel costs: specific rules
  Travel distance calculator (one-way travel):
  http://ec.europa.eu/programmes/erasmus-plus/tools/distance_en.htm
  Calculation unit cost corresponding to applicable distance band
  7 distance bands (see Annex I of Guidelines)
From home institution to venue of activity
(project beneficiaries' countries) and return

## Slide 35: Travel costs: specific rules examples
  Case 1
  Participant from Madrid (ES) takes part in activity in Rome (IT)
  Madrid - Rome (1365 Km): unit cost (distance band 500/1999 Km): 275 €
  Case 2
  Participant from Madrid takes part in activities first in Rome and then in Kiev (circular travel)*
  Madrid - Rome (1365 Km): unit cost (distance band 500/1999 Km): 275 €
  +
Rome – Kiev (1680 Km): unit cost (distance band 500/1999 Km): 275 €
= 550€
* Not applicable to flights with a stop-over

## Slide 36: TRAVEL COSTS 4 meetings, 25 participants each, destination 2500 km =360 €
 | EACEA Unit costs | Real costs | Methodology applied within consortium | Balance (UC-RC)
Travel 1 | 360 | 310 | ? | 
Travel 2 | 360 | 520 | ? | 
Travel 3 | 360 | 200 | ? | 
… | … | … | … | 
Travel 100 | 360 | 300 | ? | 
scenario 1 TOTAL | 36.000 | 37.000 |  | -1.000
scenario 2 TOTAL | 36.000 | 35.000 |  | +1.000

## Slide 37: Costs of stay: specific rules
Calculation:
number of days of activities (including travel) = Number of unit costs
Unit costs for staff unit costs for students
Staff: up to 14th day/between 15th and 60th day/between 61st day and up to 3 months
  Staff/students activities outside city of their home institution
Staff | 120 € | 70 € | 50 €
DAYS | Up to 14th day | 15th – 60th | 61st – 3 months
 |  | 15th – 90th | 
Students | 55 € | 40 € | 

## Slide 38: Cost of stay: specific rules examples
A staff (Paris): activity in Brussels during 2 days (inc. travel)
Max. 2 unit costs of 120 € (TOTAL: 240 €)
A staff (Paris): activity in Brussels during 20 days (inc. travel)
Max. 14 unit costs of 120 € + 6 unit costs of 70 € (TOTAL: 2.100 €)
A student (Paris): activity in Berlin during 22 days (inc. travel)
Max. 14 unit costs of 55 € + 8 unit costs of 40 € (TOTAL: 1.090 €)

## Slide 39: Supporting documents
Travel and Costs of Stay
Individual Travel Report (EACEA templates) + Supporting documents
(e.g. travel tickets, boarding passes, invoices, receipts, proof of attendance in meetings, agendas, tangible outputs/products, minutes)*
To keep with project accounts:
*Non-exhaustive list
To send with Final Financial statement:
Any prior authorisation from the Agency

## Slide 40
  1) Can a student receive staff costs? which is the wrong answer?
          No, never
          Yes, provided that his/her contribution is in line with the scope of the project and necessary for its achievement
          Yes, provided that the student signs an ad hoc agreement with the HEI against payment
  2) A technical staff has a usual remuneration of 60 EUR per day. The corresponding daily unit cost is 55 EUR. How much must this person actually receive under the project?
  a. 60 EUR
  b. any amount higher or equal to 55 EUR
  c. it is up to the project to decide

## Slide 41
  3) If I travel from A to B, and from B to C, and back to A, what can I charge to the project:
  a. UC for distance band from A to B + UC for distance band from B to C
  b. UC for distance band from A to B + UC for distance band from B to C + distance band from C to A
  c. UC for the sum of the distances from A to B + B to C
  4) I travel to Berlin from Feb 5th to Feb 9th and I participate in a 2 days meeting (6 and 7). On the 8th I take one day off:
  a. I can charge a maximum of 2 days as costs of stay
  b. I can charge a maximum of 4 days as costs of stay
  c. I can charge a maximum of 5 days as costs of stay

## Slide 42
  4) Management of the Grant
5) Financial Reporting
6) Calculation of the Final Grant
7) Checks & Audits(Art. II.27)

## Slide 43
  4) Management of the Grant
    Grant paid on the bank account of the coordinator (Art I.5 of GA)
Methods for distributing the grant/reimbursing the costs between coordinator and partners Detailed in Partnership Agreement:
    decision on HOW to reimburse costs (in particular UC)
    decision on WHERE to pay (/to whom)
    c) decision on WHEN to pay
    No ideal / unique / imposed method >>> specific situation of each partner should be taken into account
    Payments in cash: only if no other (reasonable) possibility
    (must be justified/traceable)

## Slide 44
5) Financial Reporting
  Financial monitoring per budget heading/partner/WP during project implementation (for budget consumption)
  Statement on the use of the previous pre-financing for PR and request for second pre-financing
  Financial reporting at final report stage, supported by Audit Certificate (Report of Factual Findings on the Final Financial Report - Type II)
  Financial statements (Excel) main financial reporting tool:

## Slide 45: How to report & Monitor the consumption of your grant
Actual costs:
  Financial statement (e.g. Subcontracting)
  cbhe_2017_-_annex_vi_-_financial_statements.xlsm
Unit costs:
  Financial statement (Staff costs and Travel and Costs of stay)
  cbhe_2017_-_annex_vi_-_financial_statements.xlsm
  Supporting documents* (Joint declaration/Timesheet, Individual Travel report)
  cbhe_joint_declaration_2017.doc
  Timesheet_version_2017.xlsm
  Individual Travel Report.doc
  * Not to be sent with the report, unless requested by EACEA for further check

## Slide 46: 6) Calculation of the Final Grant
  Grant will never exceed maximum amount indicated in Grant Agreement
  FINAL GRANT
  Examination of: a. financial statements
  b. eligibility of activities implemented
  c. eligibility of declared expenses
  2) Examination of potential penalties applied on maximum Grant
  FINAL GRANT = LOWEST VALUE between maximum Grant reduced by penalty(ies) and result of examination 1
  FINAL GRANT MINUS PRE-FINANCINGS
Positive value: balance payment
Negative value: recovery amount

## Slide 47
A
Max. Grant (Anx III of GA): 850,000 €
B
Declared grant spent (in FR): 700,000 €
C
Eligible grant (after EACEA grant/activities analysis): 650,000 €
Penalties ?
(for poor performance or non-respect of visibility obligations)
NO
YES for "Poor performance"
(Minus 25% of Max Grant = 637,500 €)
FINAL GRANT
YES for "Visibility obligations"
(Minus 20% of Max Grant = 680,000 €)
Eligible grant = 650,000 €
Max grant reduced by penalty = 637,500 €
Eligible grant = 650,000 €
HOW WILL THE FINAL GRANT AMOUNT
BE DECIDED?

## Slide 48: examples (1 of 2)
 |  | Total declared expenditure |  | 
 | Max Grant awarded | CASE 1 = max. grant awarded | CASE 2 < max. grant awarded UNDERSPENT | CASE 3 > max. grant awarded OVERSPENT
I STAFF COSTS | 340.000 | 340.000 | 290.000 | 330.000
II TRAVEL COSTS | 150.000 | 150.000 | 150.000 | 150.000
III COSTS OF STAY | 150.000 | 150.000 | 150.000 | 160.000
IV EQUIPMENT | 160.000 | 160.000 | 160.000 | 170.000
V SUBCONTRACTING | 50.000 | 50.000 | 40.000 | 50.000
TOTAL GRANT (total I-V) | 850.000 |  |  | 
TOTAL DECLARED |  | 850.000 | 790.000 | 860.000
FINAL GRANT |  | 850.000 | 790.000 | 850.000

## Slide 49: examples (2 of 2)
 |  |  | CASE 4 Total declared expenditure |  | CASE 5 Total declared expenditure | 
 | Grant awarded | % TOTAL GRANT | < total grant awarded | % TOTAL GRANT AWARDED | = total grant awarded | % INCREASE
I STAFF COSTS | 340.000 | 40% | 374.000 | 44% | 340.000 | 
II TRAVEL COSTS | 150.000 | 17,6% | 150.000 |  | 202.000 | 34%
III COSTS OF STAY | 150.000 | 17,6% | 100.000 |  | 130.000 | 
IV EQUIPMENT | 160.000 | 18,8% | 160.000 |  | 150.000 | 
V SUBCONTRACTING | 50.000 | 5,9% | 0 |  | 28.000 | 
TOTAL GRANT | 850.000 |  |  |  |  | 
TOTAL DECLARED |  |  | 784.000 |  | 850.000 | (- 37.000 €) (202.000-165.000) Ineligible
FINAL GRANT |  |  | 784.000 |  | 813.000 | 

## Slide 50: 7) Checks & Audits (Art. II.27)
EACEA/Commission may carry out technical/financial checks and audits in relation to the use of the grant
During implementation of Agreement and for a period of 5 years starting from the date of payment of the balance/recovery order
Usually outsourced to external auditors
At premises of coordinator and/or partners

## Slide 51: Final messages
Transparency/Partnership Agreement
Regular monitoring/reporting
Minimum 60% of Unit costs a lot of flexibility consider the specific needs/means of your partners
In case of doubts…ASK!

## Slide 52: QUESTION NOT ANSWERED? Please contact the E+CBHE team
EACEA-EPLUS-CBHE-PROJECTS@ec.europa.eu
Don't forget to mention your project number!